## TestBed-Imp.Plan
TASK |  |  | DEPENDENCY | DURATION | START | END | RESOURCE | REMARK
C1RT TEST BED
1 | Preparation |  |  | 1 week | 2014-02-17 | 2014-02-24
1.1 |  | Site survey
1.2 |  | Implementation plan: documentation, delivery, approval
1.3 |  | CIR: documentation, delivery, approval
1.4 |  | NDD: documentation, delivery, approval
1.5 |  | SW preparation: SW kits, licenses | [5 empty] | Need to discuss if licenses available or not
2 | HW Installation / SW Setup & Configuration |  | 1.5 | 3 weeks | 2014-02-25 | 2014-03-18 |  | 1 week HW + 2 week SW
2.1 |  | Install DGU/DSLU
2.2 |  | Install SGU/SLU
2.3 |  | Install UPM
2.4 |  | Install SAPI
2.5 |  | Install ASYNCHJMS/ASYNCH BATCH
2.6 |  | Install SDP
2.7 |  | Install ORP
2.8 |  | Install Network & Load Balancer (HSBU, LBA)
2.9 |  | Install Other components: MAU, MSM, ..
3 | Network Integration and Service Integration |  | 2 | 1 week | 2014-03-19 | 2014-03-26
4 | PCAT Provisioning |  | 3 | 3 weeks | 2014-03-27 | 2014-04-17 |  | PCAT Basic provisioning
5 | SAPI Support |  |  | TBD | 2014-02-25 |  |  | Start from week#18/Nov, trigger courting
6 | 10 days training |  |  |  | 2014-02-17
Formulas:
END = [START]+7
START = [END, row above]+1

## ELCOM HW List
Part Description | Part Number | Qty
Equipment for C1RT test system for Vinaphone
Signaling Gateway Unit (HSL)-DPM3
DPM3, Single slot, 1x Processor Merom 2.17 GHz (Dual Core, CPU=T7400), 2GB (2x 1GB), HDD 1x SATA 120GB 7200RPM (EA) BIOS 1.00.08, BMC 0.1.05 | .. 69-309-0027 | 1
DPM3, Single slot, 1x Processor Merom 2.17 GHz (Dual Core, CPU=T7400), 2GB (2x 1GB), HDD 1x SATA 120GB 7200RPM (EA) BIOS 1.00.08, BMC 0.1.05 | .. 69-309-0027 | 1
Signaling Link Module - Redundant SLM
SLM RoHS | .. 68-306-0015 | 1
SLM RoHS | .. 68-306-0015 | 1
Service Logic Unit- DPM3
DPM3, Single slot, 1x Processor Merom 2.17 GHz (Dual Core, CPU=T7400), 4GB (2x 2GB), HDD 1x SATA 120GB 7200RPM (EA) BIOS 1.00.08, BMC 0.1.05 | .. 69-309-0028 | 13
DPM3, Single slot, 1x Processor Merom 2.17 GHz (Dual Core, CPU=T7400), 2GB (2x 1GB), HDD 1x SATA 120GB 7200RPM (EA) BIOS 1.00.08, BMC 0.1.05 | .. 69-309-0027 | 2
Rating Database
IBM High-End SDP (DC) - IBM P5 p570
Server, IBM 9117 570 p5-570 2.2GHz 2-Way POWER5 Hard disk 5*73GB Disk 16GB Memory pSeries RS6000. Includes Rails/DVD | .. 48-230-8166 | 1
Network Self Service
IVRU Control Unit- DPM3
DPM3, Single slot, 1x Processor Merom 2.17 GHz (Dual Core, CPU=T7400), 2GB (2x 1GB), HDD 1x SATA 120GB 7200RPM (EA) BIOS 1.00.08, BMC 0.1.05 | .. 69-309-0027 | 1
Comverse Media Server- DPM3
DPM3, Single slot, 1x Processor Merom 2.17 GHz (Dual Core, CPU=T7400), 2GB (2x 1GB), HDD 1x SATA 120GB 7200RPM (EA) BIOS 1.00.08, BMC 0.1.05 | .. 69-309-0027 | 1
Call Control Server- DPM3
DPM3, Single slot, 1x Processor Merom 2.17 GHz (Dual Core, CPU=T7400), 2GB (2x 1GB), HDD 1x SATA 120GB 7200RPM (EA) BIOS 1.00.08, BMC 0.1.05 | .. 69-309-0027 | 1
DPM3, Single slot, 1x Processor Merom 2.17 GHz (Dual Core, CPU=T7400), 2GB (2x 1GB), HDD 1x SATA 120GB 7200RPM (EA) BIOS 1.00.08, BMC 0.1.05 | .. 69-309-0027 | 1
Signaling Link Module - Redundant SLM
SLM RoHS | .. 68-306-0015 | 1
SLM RoHS | .. 68-306-0015 | 1
Operations, Administration & Maintenance
Maintenance Access Unit
Server , Intel NSC2U (Ballenger) , 2xDC PS ,1x CPU LV5128 - Dual Core , 1.86GHZ/1066MHZ , L2=4MB , 2GB 2x1GB ECC-FBD, 4x LAN (2x LAN OB +2x LAN mezzanine), 2U, support SATA & Quad Core CPU | .. 48-230-8294 | 1
Management System Manager
DPM3, Single slot, 1x Processor Merom 2.17 GHz (Dual Core, CPU=T7400), 2GB (2x 1GB), HDD 1x SATA 120GB 7200RPM (EA) BIOS 1.00.08, BMC 0.1.05 | .. 69-309-0027 | 1
Remote Maintenance Unit
DPM3, Single slot, 1x Processor Merom 2.17 GHz (Dual Core, CPU=T7400), 2GB (2x 1GB), HDD 1x SATA 120GB 7200RPM (EA) BIOS 1.00.08, BMC 0.1.05 | .. 69-309-0027 | 1
Remote Service & Trilogue Manager
Server, Intel Langley-Irwindale DC, s.core, 2x3.2GHz/800MHz, 2MB-L2, Without HDD,2GB(2x1GB) DDR2 SDRAM, 1200Watt, 2 xDC PS, 2xHeatsink, 1x LP PCI-X riser,1x HP PCI-X riser,CD-ROM, 2U | .. 48-230-8051 | 1
CDTU2 (CD&DAT72 Unit with PS) Assembly | .. 68-204-0002 | 1
Server, Intel Langley-Irwindale DC, s.core, 2x3.2GHz/800MHz, 2MB-L2, Without HDD,2GB(2x1GB) DDR2 SDRAM, 1200Watt, 2 xDC PS, 2xHeatsink, 1x LP PCI-X riser,1x HP PCI-X riser,CD-ROM, 2U | .. 48-230-8051 | 1
CDTU2 (CD&DAT72 Unit with PS) Assembly | .. 68-204-0002 | 1
Multi Tech RCU
I/O, MultiModem ZPX Internal V.92 , PCI | .. 48-021-9388 | 1
Fujitsu MKU
RoHS - MKU (Fujitsu) | .. 48-230-0510 | 1
Minicom OUM
OUM - 1U Minicom KVM Switching Shelf | .. 68-236-1003 | 1
Network & Load Balancers
High Speed Backbone Unit (Redundant)
Cisco Catalyst 4948 Switch-DC-SMI | .. 68-342-0016 | 1
Cisco Catalyst 4948 Switch-DC-SMI | .. 68-342-0016 | 1
Redundant Load Balancer Assembly
Network Switch ,LBA AS1 WSD, DC,8x10/100B-T(RJ45),2x1000GE(SC),256Mb,1U | .. 48-110-2127 | 1
Network Switch ,LBA AS1 WSD, DC,8x10/100B-T(RJ45),2x1000GE(SC),256Mb,1U | .. 48-110-2127 | 1
OSS Cabinet
HEC 1000 Cabinet | 92-000-1000*1034882 | 1
Storage, RAID1/3/5, EMC CX300, 15x73GB/15K/4GB, 3U, 2GB FC(LC), DC | .. 48-060-9212 | 1
PDU2, 2x50A Power Inputs (Base w/o C.B) | .. 68-211-1005 | 1
PDU2, 2x50A Power Inputs (Base w/o C.B) | .. 68-211-1005 | 1
Note on A41: HANH:

## HW Summary
No. | HW Type | Description | PN | Qty
1 | DPM3 | DPM3, Single slot, 1x Processor Merom 2.17 GHz (Dual Core, CPU=T7400), 2GB (2x 1GB), HDD 1x SATA 120GB 7200RPM (EA) BIOS 1.00.08, BMC 0.1.05 | 69-309-0027 | 10
2 | DPM3 | DPM3, Single slot, 1x Processor Merom 2.17 GHz (Dual Core, CPU=T7400), 4GB (2x 2GB), HDD 1x SATA 120GB 7200RPM (EA) BIOS 1.00.08, BMC 0.1.05 | 69-39-0028 | 13
3 | SLM | SLM RoHS | 68-306-0015 | 4
4 | IBM P5 p570 | Server, IBM 9117 570 p5-570 2.2GHz 2-Way POWER5 Hard disk 5*73GB Disk 16GB Memory pSeries RS6000. Includes Rails/DVD | 48-230-8166 | 1
5 | Intel NSC2U (Ballenger) | Server , Intel NSC2U (Ballenger) , 2xDC PS ,1x CPU LV5128 - Dual Core , 1.86GHZ/1066MHZ , L2=4MB , 2GB 2x1GB ECC-FBD, 4x LAN (2x LAN OB +2x LAN mezzanine), 2U, support SATA & Quad Core CPU | 48-230-8294 | 1
6 | Intel Langley-Irwindale | Server, Intel Langley-Irwindale DC, s.core, 2x3.2GHz/800MHz, 2MB-L2, Without HDD,2GB(2x1GB) DDR2 SDRAM, 1200Watt, 2 xDC PS, 2xHeatsink, 1x LP PCI-X riser,1x HP PCI-X riser,CD-ROM, 2U | 48-230-8051 | 2
7 | CD&DAT72 | CD&DAT72 | 68-204-0002 | 2
8 | RCU (MultiModem ZPX) | RCU (MultiModem ZPX) | 48-021-9388 | 1
9 | MKU Fujitsu | MKU Fujitsu | 48-230-0510 | 1
10 | KVM Minicom | KVM Minicom | 68-236-1003 | 1
11 | HSBU Cisco Catalyst 4948 | Cisco Catalyst 4948 Switch-DC-SMI | 68-342-0016 | 2
12 | LBA AS1 WSD (Network Switch) | Network Switch ,LBA AS1 WSD, DC,8x10/100B-T(RJ45),2x1000GE(SC),256Mb,1U | 48-110-2127 | 2
13 | Storage RADI1/3/5 EMC CX300 | Storage, RAID1/3/5, EMC CX300, 15x73GB/15K/4GB, 3U, 2GB FC(LC), DC | 48-060-9212 | 1
14 | PDU2 | PDU2 | 68-211-1005 | 2
15 | HEC 1000 Cabinet | HEC 1000 Cabinet | 92-000-1000*1034882 | 1